## Sprint1
|  |  |  | Week #1 (7 hrs / week) | [6 empty] | Week #2 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours =7X4X2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15
Ideal Burndown
|  |  | 56 | [14 empty] | Remaining Hrs (Total)
Initial Understanding of requirements and set up | Tech stack decision - ReactJS, Java, MySQL, AWS, Git, Eclipse and VSCode | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 1; Week #1 (7 hrs / week) D3: 1; Week #1 (7 hrs / week) D4: 0; Week #1 (7 hrs / week) D5: 0; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Environment Set up | All | 6 | Week #1 (7 hrs / week) D1: 6; Week #1 (7 hrs / week) D2: 6; Week #1 (7 hrs / week) D3: 5; Week #1 (7 hrs / week) D4: 4; Week #1 (7 hrs / week) D5: 3; Week #1 (7 hrs / week) D6: 1; Week #1 (7 hrs / week) D7: 0
| Java Project Structure | All | 3 | Week #1 (7 hrs / week) D1: 3; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 2; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 2; Week #1 (7 hrs / week) D6: 1; Week #1 (7 hrs / week) D7: 0
| Requirement Analysis | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 3; Week #1 (7 hrs / week) D5: 2; Week #1 (7 hrs / week) D6: 2; Week #1 (7 hrs / week) D7: 0
| Architecture Diagram | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 4; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 0; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Learning and knowledge transfer of React | All | 3 | Week #1 (7 hrs / week) D1: 3; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 1; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Learning and KT of Java | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 1; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Learning and KT of MySQL | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 4; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 3; Week #1 (7 hrs / week) D5: 2; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
Application Flow and Database Design | Class Diagram | All | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 1 | 1 | 1 | 0 | 0
| Design Database Schema | All | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 2 | 1 | 1 | 0 | 0 | 0
| Application flow | All | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 2 | 0 | 0 | 0
| UI pages determination | All | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 2 | 2 | 0
|  | Total | 56 | 56 | 51 | 47 | 42 | 35 | 28 | 24 | 19 | 13 | 8 | 8 | 3 | 2 | 0
|  | Ideal | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Anusha | 7 hours / Week
Ashika | 7 hours / Week
Ramya | 7 hours / Week
Shruthi | 7 hours / Week | bar: Week #1 (7 hrs / week) D5

## Sprint2
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29
56
Database Design, Wireframes, API | Wireframes for Login Page and signup | Shruthi | 3 | 2022-03-16: 3; 2022-03-17: 2; 2022-03-18: 3; 2022-03-19: 2; 2022-03-20: 1; 2022-03-21: 0; 2022-03-22: 0
| Wireframe for Search page,booking details | Shruthi | 3 | 2022-03-16: 3; 2022-03-17: 3; 2022-03-18: 0; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Wireframe for HotelList page | Shruthi | 2 | 2022-03-16: 2; 2022-03-17: 2; 2022-03-18: 2; 2022-03-19: 2; 2022-03-20: 1; 2022-03-21: 1; 2022-03-22: 0
| Wireframe for confirmation screen | Ashika | 3 | 2022-03-16: 3; 2022-03-17: 3; 2022-03-18: 2; 2022-03-19: 1; 2022-03-20: 1; 2022-03-21: 0; 2022-03-22: 0
| Wireframe for cancellation screen | Ashika | 3 | 2022-03-16: 3; 2022-03-17: 1; 2022-03-18: 2; 2022-03-19: 1; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Database setup in RDS | Ramya and Anusha | 5 | 2022-03-16: 5; 2022-03-17: 3; 2022-03-18: 3; 2022-03-19: 3; 2022-03-20: 1; 2022-03-21: 1; 2022-03-22: 0
| Creation of tables for User,Customer,Employee and Booking | Anusha | 3 | 2022-03-16: 3; 2022-03-17: 2; 2022-03-18: 1; 2022-03-19: 1; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Creation of tables for hotels,rooms,rewards,amenities | Ramya | 3 | 2022-03-16: 3; 2022-03-17: 2; 2022-03-18: 2; 2022-03-19: 1; 2022-03-20: 1; 2022-03-21: 0; 2022-03-22: 0
| Populating mock data for the tables | Ramya and Anusha | 3 | 2022-03-16: 3; 2022-03-17: 2; 2022-03-18: 1; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
Setup Frontend Code, Routing, and API | Frontend setup in React | Shruthi and Ashika | 3 | 2022-03-16: 3; 2022-03-17: 0; 2022-03-18: 0; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Routing setup | Shruthi and Ashika | 2 | 2022-03-16: 2; 2022-03-17: 2; 2022-03-18: 0; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Integration of react app with AWS Cognito | Shruthi | 2 | 2022-03-16: 2; 2022-03-17: 2; 2022-03-18: 2; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Implementation of Login Screen | Shruthi | 3 | 2022-03-16: 3; 2022-03-17: 3; 2022-03-18: 3; 2022-03-19: 3; 2022-03-20: 2; 2022-03-21: 1; 2022-03-22: 0
| Development of DAO layer | Anusha and Ramya | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 2 | 0 | 0 | 0 | 0
| Development of POST Login/Register API | Anusha | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0
| Development of GET hotel API | Ramya | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0
| Implementation of confirmation | Ashika | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 1 | 0
| Implementation of Cancellation screen | Ashika | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0
|  | Total | 56 | 56 | 45 | 39 | 32 | 25 | 21 | 18 | 16 | 16 | 12 | 5 | 3 | 3 | 0
|  | Ideal | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0

## Sprint3
|  |  |  | Week #5(7 hrs / week) | [6 empty] | Week #6(7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours =7X4X2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12
Ideal Burndown
|  |  | 56 | [14 empty] | Remaining Hrs (Total)
Front End Development | Cognito Setup in AWS | Shruthi | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of Cognito with Login | Shruthi | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of Cognito with Registration | Shruthi | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of Registration Page | Shruthi | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of POST register api | Shruthi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| Integration of POST saveCustomer api | Shruthi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Integration of POST login api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Design and implementation of Search page | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of NavBar Component | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of all bookings page | Ashika | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integrating get all bookings api | Ashika | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| integrating edit booking for a customer | Ashika | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integrating delete booking api for the customer | Ashika | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Designing and implementing profile screen | Ashika | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Integrating profile details for the customer | Ashika | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
| Getting all login details for a customer | Ashika | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
Backend Development | Design checkRoomAvailability API | Ramya | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement getHotel API | Ramya | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement getHotelRooms | Ramya | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement getHotelBooking | Ramya | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Design getAmenities Price API | Ramya | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Design dynamic Pricing | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0
| Implement checkRoomAvailablity API | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
| Designing Booking API's | Anusha | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement register API | Anusha | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Implement Login API for Customer/Employee | Anusha | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Implement User API based on the roles | Anusha | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Development of DAO layer for Booking API's | Anusha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Designing of All bookings for customers/employee | Anusha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Total | 56 | 56 | 52 | 46 | 41 | 38 | 35 | 29 | 23 | 19 | 15 | 11 | 7 | 4 | 0
|  | Ideal | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0

## Sprint4
|  |  |  | Week #7 (7 hrs / week) | [6 empty] | Week #8(7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours =7X4X2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10
Ideal Burndown
|  |  | 56 | [14 empty] | Remaining Hrs (Total)
Front End Development | Design and implementation of HotelList Page | Shruthi | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of RoomDetails Page | Shruthi | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of Booking Details Page | Shruthi | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of GET hotelsByCity api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of GET roomsByHotelId api | Shruthi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of GET amenitiesByHotelId api | Shruthi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of GET amentiesPrice api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Integration of POST saveBooking api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Integration of POST rewards api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Design and implementation of DisplayInfo Component | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Designing Employee View | Ashika | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Implementation of all customers for an hotel view | Ashika | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Integration of GET all customers for an hotel api | Ashika | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Integration of DELETE booking of a customer | Ashika | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of Update Rewards for a customer | Ashika | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Integration testing of the entire flow | Ashika | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| unit testing allbookings page | Ashika | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| unit testing all customers page | Ashika | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| unit testing profile page | Ashika | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backend Development | UI integration for hotel api | Ramya | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UI integration for Room api | Ramya | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UI integration for Ameties api | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bug Fixes on all backend api | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Deployment in AWS | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
| DB Script to populate Data | Ramya | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0
| Testing of all backend apis | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| UI Integration of Login/Registration API | Anusha | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UI Integration of User API | Anusha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Development of Booking API's | Anusha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| UI integration of Booking API's | Anusha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
| Deployment of API's in AWS | Anusha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0
| Testing all API's w.r.t Postman | Anusha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Total | 56 | 56 | 52 | 48 | 43 | 39 | 35 | 30 | 26 | 21 | 17 | 13 | 8 | 5 | 0
|  | Ideal | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0