## Sprint1
|  |  |  | Week #1 (7 hrs / week) | [6 empty] | Week #2 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours =7X4X2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15
Ideal Burndown
|  |  | 56 | [14 empty] | Remaining Hrs (Total)
Initial Understanding of requirements and set up | Tech stack decision - ReactJS, Java, MySQL, AWS, Git, Eclipse and VSCode | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 1; Week #1 (7 hrs / week) D3: 1; Week #1 (7 hrs / week) D4: 0; Week #1 (7 hrs / week) D5: 0; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Environment Set up | All | 6 | Week #1 (7 hrs / week) D1: 6; Week #1 (7 hrs / week) D2: 6; Week #1 (7 hrs / week) D3: 5; Week #1 (7 hrs / week) D4: 4; Week #1 (7 hrs / week) D5: 3; Week #1 (7 hrs / week) D6: 1; Week #1 (7 hrs / week) D7: 0
| Java Project Structure | All | 3 | Week #1 (7 hrs / week) D1: 3; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 2; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 2; Week #1 (7 hrs / week) D6: 1; Week #1 (7 hrs / week) D7: 0
| Requirement Analysis | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 3; Week #1 (7 hrs / week) D5: 2; Week #1 (7 hrs / week) D6: 2; Week #1 (7 hrs / week) D7: 0
| Architecture Diagram | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 4; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 0; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Learning and knowledge transfer of React | All | 3 | Week #1 (7 hrs / week) D1: 3; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 1; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Learning and KT of Java | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 1; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Learning and KT of MySQL | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 4; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 3; Week #1 (7 hrs / week) D5: 2; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
Application Flow and Database Design | Class Diagram | All | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 1 | 1 | 1 | 0 | 0
| Design Database Schema | All | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 2 | 1 | 1 | 0 | 0 | 0
| Application flow | All | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 2 | 0 | 0 | 0
| UI pages determination | All | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 2 | 2 | 0
|  | Total | 56 | 56 | 51 | 47 | 42 | 35 | 28 | 24 | 19 | 13 | 8 | 8 | 3 | 2 | 0
|  | Ideal | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Anusha | 7 hours / Week
Ashika | 7 hours / Week
Ramya | 7 hours / Week
Shruthi | 7 hours / Week
|  |  | XP Values followed | Week #1 (7 hrs / week) D2: Feedback
Communication
Sit Together
Simplicity
Established strong communication since the beginning of the project, We communicated individual strengths and experience about particular technologies and used it to decide our technology stack
We have kept our components modular and design simple so that it is easier to maintain, support, and revise.

## Sprint2
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29
56
Database Design, Wireframes, API | Wireframes for Login Page and signup | Shruthi | 3 | 2022-03-16: 3; 2022-03-17: 2; 2022-03-18: 3; 2022-03-19: 2; 2022-03-20: 1; 2022-03-21: 0; 2022-03-22: 0
| Wireframe for Search page,booking details | Shruthi | 3 | 2022-03-16: 3; 2022-03-17: 3; 2022-03-18: 0; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Wireframe for HotelList page | Shruthi | 2 | 2022-03-16: 2; 2022-03-17: 2; 2022-03-18: 2; 2022-03-19: 2; 2022-03-20: 1; 2022-03-21: 1; 2022-03-22: 0
| Wireframe for confirmation screen | Ashika | 3 | 2022-03-16: 3; 2022-03-17: 3; 2022-03-18: 2; 2022-03-19: 1; 2022-03-20: 1; 2022-03-21: 0; 2022-03-22: 0
| Wireframe for cancellation screen | Ashika | 3 | 2022-03-16: 3; 2022-03-17: 1; 2022-03-18: 2; 2022-03-19: 1; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Database setup in RDS | Ramya and Anusha | 5 | 2022-03-16: 5; 2022-03-17: 3; 2022-03-18: 3; 2022-03-19: 3; 2022-03-20: 1; 2022-03-21: 1; 2022-03-22: 0
| Creation of tables for User,Customer,Employee and Booking | Anusha | 3 | 2022-03-16: 3; 2022-03-17: 2; 2022-03-18: 1; 2022-03-19: 1; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Creation of tables for hotels,rooms,rewards,amenities | Ramya | 3 | 2022-03-16: 3; 2022-03-17: 2; 2022-03-18: 2; 2022-03-19: 1; 2022-03-20: 1; 2022-03-21: 0; 2022-03-22: 0
| Populating mock data for the tables | Ramya and Anusha | 3 | 2022-03-16: 3; 2022-03-17: 2; 2022-03-18: 1; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
Setup Frontend Code, Routing, and API | Frontend setup in React | Shruthi and Ashika | 3 | 2022-03-16: 3; 2022-03-17: 0; 2022-03-18: 0; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Routing setup | Shruthi and Ashika | 2 | 2022-03-16: 2; 2022-03-17: 2; 2022-03-18: 0; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Integration of react app with AWS Cognito | Shruthi | 2 | 2022-03-16: 2; 2022-03-17: 2; 2022-03-18: 2; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0
| Implementation of Login Screen | Shruthi | 3 | 2022-03-16: 3; 2022-03-17: 3; 2022-03-18: 3; 2022-03-19: 3; 2022-03-20: 2; 2022-03-21: 1; 2022-03-22: 0
| Development of DAO layer | Anusha and Ramya | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 2 | 0 | 0 | 0 | 0
| Development of POST Login/Register API | Anusha | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0
| Development of GET hotel API | Ramya | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0
| Implementation of confirmation | Ashika | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 1 | 0
| Implementation of Cancellation screen | Ashika | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0
|  | Total | 56 | 56 | 45 | 39 | 32 | 25 | 21 | 18 | 16 | 16 | 12 | 5 | 3 | 3 | 0
|  | Ideal | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Anusha | 7 hours / Week
Ashika | 7 hours / Week
Ramya | 7 hours / Week
Shruthi | 7 hours / Week
|  | XP Values followed | Communication
Sit Together
Simplicity

## Sprint3
|  |  |  | Week #5(7 hrs / week) | [6 empty] | Week #6(7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours =7X4X2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12
Ideal Burndown
|  |  | 56 | [14 empty] | Remaining Hrs (Total)
Front End Development | Cognito Setup in AWS | Shruthi | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of Cognito with Login | Shruthi | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of Cognito with Registration | Shruthi | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of Registration Page | Shruthi | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of POST register api | Shruthi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| Integration of POST saveCustomer api | Shruthi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Integration of POST login api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Design and implementation of Search page | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of NavBar Component | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of all bookings page | Ashika | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integrating get all bookings api | Ashika | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| integrating edit booking for a customer | Ashika | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integrating delete booking api for the customer | Ashika | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Designing and implementing profile screen | Ashika | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Integrating profile details for the customer | Ashika | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
| Getting all login details for a customer | Ashika | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
Backend Development | Design checkRoomAvailability API | Ramya | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement getHotel API | Ramya | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement getHotelRooms | Ramya | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement getHotelBooking | Ramya | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Design getAmenities Price API | Ramya | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Design dynamic Pricing | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0
| Implement checkRoomAvailablity API | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
| Designing Booking API's | Anusha | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement register API | Anusha | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Implement Login API for Customer/Employee | Anusha | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Implement User API based on the roles | Anusha | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Development of DAO layer for Booking API's | Anusha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Designing of All bookings for customers/employee | Anusha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Total | 56 | 56 | 52 | 46 | 41 | 38 | 35 | 29 | 23 | 19 | 15 | 11 | 7 | 4 | 0
|  | Ideal | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Anusha | 7 hours / Week
Ashika | 7 hours / Week
Ramya | 7 hours / Week
Shruthi | 7 hours / Week
|  |  | XP Values followed | 2022-03-31: Communication
Sit Together
Simplicity
Pair programming
Feedback
2-weeks sprint/bi-weekly cycle

## Sprint4
|  |  |  | Week #7 (7 hrs / week) | [6 empty] | Week #8(7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours =7X4X2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10
Ideal Burndown
|  |  | 56 | [14 empty] | Remaining Hrs (Total)
Front End Development | Design and implementation of HotelList Page | Shruthi | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of RoomDetails Page | Shruthi | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design and implementation of Booking Details Page | Shruthi | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of GET hotelsByCity api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of GET roomsByHotelId api | Shruthi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of GET amenitiesByHotelId api | Shruthi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of GET amentiesPrice api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Integration of POST saveBooking api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Integration of POST rewards api | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Design and implementation of DisplayInfo Component | Shruthi | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Designing Employee View | Ashika | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Implementation of all customers for an hotel view | Ashika | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Integration of GET all customers for an hotel api | Ashika | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Integration of DELETE booking of a customer | Ashika | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration of Update Rewards for a customer | Ashika | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Integration testing of the entire flow | Ashika | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| unit testing allbookings page | Ashika | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| unit testing all customers page | Ashika | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| unit testing profile page | Ashika | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backend Development | UI integration for hotel api | Ramya | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UI integration for Room api | Ramya | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UI integration for Ameties api | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bug Fixes on all backend api | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Deployment in AWS | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
| DB Script to populate Data | Ramya | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0
| Testing of all backend apis | Ramya | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| UI Integration of Login/Registration API | Anusha | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UI Integration of User API | Anusha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Development of Booking API's | Anusha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| UI integration of Booking API's | Anusha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
| Deployment of API's in AWS | Anusha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0
| Testing all API's w.r.t Postman | Anusha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Total | 56 | 56 | 52 | 48 | 43 | 39 | 35 | 30 | 26 | 21 | 17 | 13 | 8 | 5 | 0
|  | Ideal | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Anusha | 7 hours / Week
Ashika | 7 hours / Week
Ramya | 7 hours / Week |  |  | 2022-04-28: XP Values followed; 2022-04-30: Communication
Shruthi | 7 hours / Week |  |  | 2022-04-30: Sit Together
Simplicity
Pair programming
Feedback
2-weeks sprint/bi-weekly cycle