## Sprint
|  |  |  | Week #1 (7 hrs / week) | [6 empty] | Week #2 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours =7X4X2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15
Ideal Burndown
|  |  | 56 | [14 empty] | Remaining Hrs (Total)
Initial Understanding of requirements and set up | Tech stack decision - ReactJS, Java, MySQL, AWS, Git, Eclipse and VSCode | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 1; Week #1 (7 hrs / week) D3: 1; Week #1 (7 hrs / week) D4: 0; Week #1 (7 hrs / week) D5: 0; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Environment Set up | All | 6 | Week #1 (7 hrs / week) D1: 6; Week #1 (7 hrs / week) D2: 6; Week #1 (7 hrs / week) D3: 5; Week #1 (7 hrs / week) D4: 4; Week #1 (7 hrs / week) D5: 3; Week #1 (7 hrs / week) D6: 1; Week #1 (7 hrs / week) D7: 0
| Java Project Structure | All | 3 | Week #1 (7 hrs / week) D1: 3; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 2; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 2; Week #1 (7 hrs / week) D6: 1; Week #1 (7 hrs / week) D7: 0
| Requirement Analysis | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 3; Week #1 (7 hrs / week) D5: 2; Week #1 (7 hrs / week) D6: 2; Week #1 (7 hrs / week) D7: 0
| Architecture Diagram | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 4; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 0; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Learning and knowledge transfer of React | All | 3 | Week #1 (7 hrs / week) D1: 3; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 1; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Learning and KT of Java | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 3; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 2; Week #1 (7 hrs / week) D5: 1; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
| Learning and KT of MySQL | All | 4 | Week #1 (7 hrs / week) D1: 4; Week #1 (7 hrs / week) D2: 4; Week #1 (7 hrs / week) D3: 3; Week #1 (7 hrs / week) D4: 3; Week #1 (7 hrs / week) D5: 2; Week #1 (7 hrs / week) D6: 0; Week #1 (7 hrs / week) D7: 0
Application Flow and Database Design | Class Diagram | All | 5 | Week #1 (7 hrs / week) D1: 5; Week #1 (7 hrs / week) D2: 5; Week #1 (7 hrs / week) D3: 5; Week #1 (7 hrs / week) D4: 5; Week #1 (7 hrs / week) D5: 5; Week #1 (7 hrs / week) D6: 5; Week #1 (7 hrs / week) D7: 5
| Design Database Schema | All | 6 | Week #1 (7 hrs / week) D1: 6; Week #1 (7 hrs / week) D2: 6; Week #1 (7 hrs / week) D3: 6; Week #1 (7 hrs / week) D4: 6; Week #1 (7 hrs / week) D5: 6; Week #1 (7 hrs / week) D6: 6; Week #1 (7 hrs / week) D7: 6
| Application flow | All | 6 | Week #1 (7 hrs / week) D1: 6; Week #1 (7 hrs / week) D2: 6; Week #1 (7 hrs / week) D3: 6; Week #1 (7 hrs / week) D4: 6; Week #1 (7 hrs / week) D5: 6; Week #1 (7 hrs / week) D6: 6; Week #1 (7 hrs / week) D7: 6
| UI pages determination | All | 7 | Week #1 (7 hrs / week) D1: 7; Week #1 (7 hrs / week) D2: 7; Week #1 (7 hrs / week) D3: 7; Week #1 (7 hrs / week) D4: 7; Week #1 (7 hrs / week) D5: 7; Week #1 (7 hrs / week) D6: 7; Week #1 (7 hrs / week) D7: 7
|  | Total | 56 | Week #1 (7 hrs / week) D1: 56; Week #1 (7 hrs / week) D2: 51; Week #1 (7 hrs / week) D3: 47; Week #1 (7 hrs / week) D4: 42; Week #1 (7 hrs / week) D5: 35; Week #1 (7 hrs / week) D6: 28; Week #1 (7 hrs / week) D7: 24
|  | Ideal | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Team:
Anusha | 7 hours / Week
Ashika | 7 hours / Week
Ramya | 7 hours / Week
Shruthi | 7 hours / Week
Total Available Hours During Sprint: | 28
XP Values followed | Communication
Sit Together
Simplicity
Established strong communication since the beginning of the project, We communicated individual strengths and experience about particular technologies and used it to decide our technology stack
We have kept our components modular and design simple so that it is easier to maintain, support, and revise.